## Budget
PROJECT TRACKING TEMPLATE
Project name: | Acne studios website build | Manager: | Jon Snow
Scope document link: | link | Over / under | 2550
Hourly rate | 150 | Progress |  |  |  |  | 0%
Task ID | Task name |  | Assigned to | Status | Start date | End date | Estimated hours | Estimated cost | Actual hours | Actual cost | Over / under
1.1 | Task 1 |  | Bradley | To do | 2022-11-09 | 2022-11-30 | 4 | 600 | 3 | 450 | 150
1.2 | Task 2 |  | Derek | To do | 2022-11-10 | 2022-12-01 | 6 | 900 | 8 | 1200 | -300
1.3 | Task 3 |  | Anna | To do | 2022-11-11 | 2022-12-02 | 6 | 900 | 0 | 0 | 900
1.4 | Task 4 |  | Cecile | To do | 2022-11-29 | 2022-11-23 | 12 | 1800 | 0 | 0 | 1800
[8 empty] | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
[8 empty] | 0 |  | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
Totals | [6 empty] | 28 | 4200 | 11 | 1650 | 2550

## Tracker
PROJECT TRACKER TEMPLATE
Task name | Hours worked | Reported by | On date
Task 1 | 3 | Bradley | 2022-12-15
Task 2 | 8 | Cecile | 2022-12-15

## Master
Team | Status | Working hours/Day
Anna | To do | 8
Bradley | In progress
Cecile | Done
Derek | To do
Emma